## Trang tính1
Task assignment - Team 02 (Capstone_2_JS)
No | Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
USER SIDE
1 | UI / Resposive | 2024-02-17 | 2024-02-21 | 100% | Trần Anh Tuấn | 2024-02-26 | 2024-02-29 | 100% | Vũ Thị Thanh Hồng
2 | API resource for the cart | 2024-02-22 | 2024-02-22 | 100% |  |  |  | 100%
3 | Class of product object | 2024-02-22 | 2024-02-22 | 100% |  |  |  | 100%
4 | Display products to customers | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
5 | Dropdown list for filtering by brands | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
6 | Add products to the cart | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
7 | Display cart in the screen | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
8 | button of changing quantity in cart | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
9 | Display total amount | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
10 | After 'pay' button is pressed, the cart will be emptied. | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
11 | remove products from the cart | 2024-02-22 | 2024-02-25 | 100% |  |  |  | 100%
ADMIN SIDE
12 | UI/Resposive | 2024-02-19 | 2024-02-19 | 100% | Vũ Thị Thanh Hồng | 2024-02-26 | 2024-02-29 | 100% | Trần Anh Tuấn
13 | API resource for products | 2024-02-20 | 2024-02-21 | 100% |  |  |  | 100%
14 | Call API to display, add, remove & update products | 2024-02-21 | 2024-02-22 | 100% |  |  |  | 100%
15 | Validation | 2024-02-25 | 2024-02-28 | 100% |  |  |  | 100%
16 | Search by name | 2024-02-23 | 2024-02-24 | 100% |  |  |  | 100%
17 | Sort by price | 2024-02-24 | 2024-02-25 | 100% |  |  |  | 100%